## Sprint plan 186
| Priority | Member 1 | Member 2 |  |  | Questions | Chandra sir's answers |  | Problem Definition | User acceptance criteria/trust | Acceptance Checklist
Agents
Planner/Customer Support Agent | P0 | Prem | Swara | [5 empty] | Acts as the brainstorming front door for the homeowner: takes a vague ask (“build me a house”) and turns it into a structured brief, square footage, BHK count, budget range, and lot. Does not enforce hard rules; it just plans and scopes the project before generation starts. | Given a free text request, must capture house size, room count/type, and budget into a structured spec without ever fabricating a constraint value (those come from the Constraint Agent). Must support template selection (e.g. “2BHK”/“3BHK”) so the user can skip manual layout out. Must hand off a complete, unambiguous brief to the Generator Agent, incomplete briefs must trigger a clarifying question, not a silent guess. Must integrate with Templatization (backlog) so saved templates can be loaded as a starting brief. | ☐ Captures square footage, BHK count, and budget range in every intake, with no field left silently blank ☐ Never invents a constraint value itself (setbacks, coverage %), always defers to Constraint/Location Zoning Agent ☐ Triggers a clarifying question when the brief is incomplete, instead of guessing and passing it forward ☐ Supports loading a saved template (2BHK/3BHK etc.) as a starting brief ☐ Final brief handed to Generator Agent is structured JSON, not free text ☐ Response time to user's initial prompt < 5 seconds before first follow-up question ☐ Disambiguates location BEFORE Agent Manager starts any work e.g. asks “Redmond, WA or Redmond, CA?” then narrows to exact ZIP (98004 vs 98104) so the right constraint set loads ☐ When Agent Manager flags missing info mid-run, surfaces a clear question to the user and states its own assumption before proceeding (not a silent guess) ☐ Receives state updates from Agent Manager and simplifies them for the user. never leaks raw internal agent/tool names or errors to the end user
Agent Manager | P0 | Swara | Prem |  |  | Swara: Q1. What is the exact pipeline order- which agent runs when, what runs in parallel and what's conditional? Q2. What is the specific input and output format for each agent? Need this to define the state object. | Q1: we have to define the orchestration. Could you come up with an initial proposal? Q2: Anupam? |  | The orchestrator that decides which agent runs next and in what order, Generator, Verifier, Location, Constraint, Reviewer, etc. So the multi agent pipeline doesn't need every agent to know about every other agent. Came directly from the team's own observation that with this many agents, someone has to own sequencing. | Must maintain the canonical pipeline order (Planner → Location/Constraint → Generator → Verifier → Reviewer/Human in the loop) and be the single place this order is defined, no agent should hardcode a call to another agent. Must support conditional branching (e.g. skip Multi floor Agent if single floor) and re entry loops (Generator ⇄ Verifier until pass). Must log which agent ran, when, and why for debuggability. Must surface a clear failure state to the UI if any agent in the chain errors out, rather than failing silently. | ☐ Pipeline order (Planner → Location/Constraint → Generator → Verifier → Reviewer) is defined in one place only — no agent hardcodes a call to another agent ☐ Supports conditional branching (e.g. skips Multi-floor Agent if user selects single floor) ☐ Supports re-entry loop: Generator ⇄ Verifier repeats automatically until a pass, with a max retry cap (no infinite loop) ☐ Logs which agent ran, at what time, and why, for every request ☐ Surfaces a clear failure state to the UI within 2 seconds of any agent erroring out — never fails silently ☐ Average end-to-end orchestration overhead (excluding individual agent compute time) < 1 second per request ☐ Knows every agent's required input/output format — individual agents do NOT need to maintain a dictionary of other agents' formats ☐ Handles formatting, validation, and state tracking centrally, not per-agent ☐ Inter-agent messages use JSON-RPC format (same pattern as MCP client/server) ☐ Maintains full live state: what's happening, who's talking to whom, current progress — queryable at any point ☐ Pushes simplified status updates to the Planner/Customer Support Agent — never exposes raw internal state directly to the end user ☐ Distinguishes agent-to-agent calls (must route through Agent Manager) from agent-to-tool calls (e.g. Site Plan Agent calling Z3 Verifier directly) — tool calls stay inside the calling agent's own code ☐ Tells Customer Support Agent to ask the user when it hits missing info mid-run, instead of guessing or stalling silently ☐ Agent clusters (frequent back-and-forth or sequential dependency groups) are explicitly mapped and documented, with a minimum common JSON field format agreed for each cluster
Site Plan Generator Agent | P0 | Devam |  |  |  | Devam:Q4: Talk With Planning Agent + UI: Need To ask user for some clarification if the buildable envelop is weird shaped and hence to finalise the Polygon on which exterior shell is to be built - Think Via CAP Theorm, on how to route the interaction with UI v/s via agent manager. Consistency (state management - agent manager)v/s Availablity . Q5 <10 sec issue: Chandra sir? Q1. Lot Geometry Validity Is the raw lot polygon from the site engineer report guaranteed to be closed, non-self-intersecting, and consistently oriented? Or should Site Plan Generator validate and repair geometry during ingestion? Q2. Exterior Shell Curve Support Are curved (arc) boundaries for the generated exterior building shell in scope for this phase, or should they be deferred to a later iteration? (Raw lot boundaries may still contain curves and will be handled accordingly.) Q3. Agent Handoff & JSON Schema What is the expected input/output format between agents? How should JSON payloads be structured and standardized across the pipeline? Clarification is needed on the JSON Extractor and shared schemas. | Q1: it's expected to be polygon. But it's always good to validate the assumption. Q2: good question. Curved surfaces are not preferred in house architecture |  | Generates the outer building envelope/footprint on the plot, the rectangle or polygon that respects setbacks, lot coverage %, and tree protection zones, before any rooms are placed inside. This is the “Agent 1” outer envelope step every group's Prob1 experiments were built around. | Output footprint must stay within the SBC setbacks and lot coverage cap for the selected jurisdiction (e.g. Seattle Downtown NR: 15/15/5 ft setbacks, 35% coverage) and must not intersect the tree protection zone. Must maximize buildable area within those constraints, not just satisfy them this was explicitly called out as a hard constraint in Z3, not a soft suggestion, after multiple groups under built. Must hand off exact polygon coordinates (not images) to the Verifier Agent, since every Prob1 finding showed models hallucinate far less on typed coordinates than on images. Must support non rectangular/L shaped lots, not just rectangles. | ☐ Output footprint stays within front/rear/side setbacks for the resolved jurisdiction zero tolerance for breach ☐ Lot coverage % stays at or under the jurisdiction's max cap (e.g. 35% for Seattle Downtown NR) ☐ Footprint never intersects the tree protection zone polygon ☐ Area utilization within the legal footprint should be > 90% of the buildable envelope (not just compliant , actually space-efficient) ☐ Supports non-rectangular / L-shaped lots, not just rectangular lots ☐ Output is exact polygon coordinates (JSON), never an image or sketch ☐ Generation time for a single footprint < 10 seconds before handoff to Verifier
Floor Plan Generator Agent | P0 | Prasad | Devank |  |  | Prasad: Q1) Are there a specific number of internal room constraints that need to be checked for a valid internal layout(the ones mentioned in the acceptance checklist) or do the internal constraints also vary according to the location? |  |  | Takes the verified footprint and tiles it into the actual interior rooms (bedrooms, kitchen, bathrooms, living room) with no overlaps and no gaps, this is the “interior layout” half of the two phase generate then verify loop the team already prototyped in Prob2. | Must place the full required room program (e.g. 3 bedrooms + 1 kitchen + 2 bathrooms + 1 living room) inside the footprint with zero overlapping area and zero uncovered gaps. Must respect adjacency rules surfaced repeatedly in Prob2 findings, bathrooms near bedrooms, bathrooms not adjacent to each other, kitchen not adjacent to bathroom, living room near the main entry. Must avoid the “stacked/long rectangle” failure mode multiple groups hit, and keep corridor area low relative to usable room area (several groups flagged corridors eating 10–40% of space as a failure). Must pass off final coordinates as a JSON file (via the Json Extractor tool) for the Verifier Agent to consume, not as a description. | ☐ Zero overlapping room area across the entire floor plan ☐ Zero uncovered/unallocated gaps within the footprint ☐ Full required room program present (e.g. 3 bedrooms + kitchen + 2 bathrooms + living room, per brief) — no room silently dropped ☐ Bathrooms are not adjacent to each other ☐ Bathrooms are not adjacent to the kitchen ☐ Each bedroom has a bathroom within reasonable proximity (per adjacency rule set) ☐ Living room is positioned near the main entry ☐ Living room area is larger than each individual bedroom's area ☐ Corridor/circulation area stays under 15% of total usable floor area (flagged failure mode: some groups hit 10–40%) ☐ Output handed to Verifier as JSON (via Json Extractor), never as a text description or image ☐ Generation-to-JSON-handoff time < 10 seconds per iteration
Multi-floor Generator Agent | P0 | Nitesh | [6 empty] | Extends single floor generation to stacked floors, keeping load bearing walls aligned floor to floor for structural strength, flagged in the meeting as one of the most complex unsolved pieces, since changing floor 1 forces a recheck of floor 2 and vice versa. | Walls on floor 2+ must align with walls on the floor below wherever structurally required (e.g. bathroom above bathroom plumbing stacks, as Nitesh's early experiment surfaced). Must rerun constraint checks on the floor below whenever the floor above changes, and iterate left to right until both floors settle, this back and forth was explicitly named as the core difficulty by the mentor. Must not silently drop rooms (e.g. missing living room/balcony) when LLM context limits are hit during multi floor generation, a failure already observed in early testing. Must clearly flag to the user when a multi floor request cannot converge rather than returning a mismatched area layout. | ☐ Load-bearing walls align floor-to-floor wherever structurally required ☐ Bathroom-above-bathroom plumbing stack alignment is checked and enforced where applicable ☐ Re-runs constraint checks on the floor below whenever the floor above changes (and vice versa) until both floors stabilize ☐ Max iteration cap defined for the floor-to-floor settling loop (no infinite back-and-forth) ☐ No room (e.g. living room, balcony) is silently dropped when LLM context limit is reached during multi-floor generation ☐ Clearly flags to the user when a multi-floor request cannot converge, rather than returning mismatched floor areas ☐ Total area per floor matches the brief's specified square footage within an agreed tolerance (e.g. ±5%)
Verifier Agent | P0 | Devam | Harshit |  |  | Devam: Q5. Packing Strategy Translation Layer Who owns the conversion of a user-selected packing strategy into structured constraints that Z3 can consume? Possible owners: * Planning Agent * Constraint Engine * New dedicated translation component Also, should packing strategy selection remain user-driven or be automated?; Q1. Constraint Tagging Strategy Can Constraint Engine attach explicit metadata to every constraint object, such as: * evaluation: shapely ¦ z3 * stage: shell ¦ room This would allow Verifier to dispatch constraints based on tags instead of inferring behavior at runtime. Q2. Z3 Repair Capability Does the shared Z3 Verifier support repair/minimal-edit mode (returning coordinate adjustments or infeasibility proofs), or does it currently provide only SAT/UNSAT feasibility checking? Q3. Z3 Optimization Scope Should the Z3 tool support optimization for room-stage packing problems, such as: * habitable area vs. corridor ratio * adjacency satisfaction * strategy feasibility evaluation Q4. Feedback to Generator Agent Does the rule "never leak corrected coordinates back to the Generator" apply specifically to Agent A1? If so, what information can safely be passed back as feedback without revealing coordinates? | Q1: think of constraint like user defined and system defined. But not sure how it'll help verifier? Sure tagging helps classify constraints Q2: Z3 will only verify. Repair needs to be handled by a separate agent. Q3: good question. No. This needs to be handled by a separate agent preferably floor plan agent. Q4: Anupam? Q5: Floor plan agent is my preference. Anupam - what do you think? |  | The mathematical referee of the system: runs the Z3 based check over whatever the Generator produced and returns a deterministic pass/fail plus the specific violated constraints the team's existing two agent (generator + verifier) loop is built around this. | Must catch every constraint violation type already observed in testing: setback breaches, lot coverage overages, tree zone intrusions, room overlaps, room area shortfalls, and adjacency violations. Feedback returned on failure must be diagnostic and specific (e.g. “move house_top_y from 61 to 65”) and must never leak the corrected coordinates back to the Generator, several groups found that leaking the answer collapses the two agent loop into one and defeats the purpose of verification. Must run the Z3 solver as part of this agent (per the mentor's explicit clarification that Z3 lives inside the Verifier Agent, even though it can also be run locally). Must handle floating point tolerance so it doesn't produce false negatives on near exact constraint satisfaction. | ☐ Catches setback breaches (front/rear/side) with zero false negatives ☐ Catches lot-coverage overages ☐ Catches tree-protection-zone intrusions ☐ Catches room-to-room overlaps ☐ Catches room-area shortfalls against minimum size requirements ☐ Catches adjacency rule violations (e.g. bathroom-bathroom, bathroom-kitchen) ☐ Returns specific, diagnostic feedback on failure (e.g. “move house_top_y from 61 to 65”) — not just pass/fail ☐ Never leaks the corrected coordinates back to the Generator Agent (would collapse the two-agent loop) ☐ Z3 solver runs as a step inside this agent, with floating-point tolerance set to avoid false-negative failures on near-exact matches ☐ Verification turnaround time < 5 seconds per submitted layout
Reviewer (City) Agent | P0 | Siddh | Rohan |  |  | Rohan: Q1. If the Reviewer has access to the same constraints and the same Z3 model as the Verifier and checklist 2 guarantees that they cannot reach a different conclusion, then what additional role or value does the Reviewer provide beyond what the Verifier has already done? Q2. The “walkthrough < 10 min” requirement suggests human involvement while “auto-reject, no override” implies full automation. So who actually makes the final approval decision: the LLM, a human reviewer, or a human validating an LLM-generated recommendation? | Q1- this needs to have deeper integration with UI and get a sign off for each wall. Something like point to each wall and ask "is this looking good?" Q2- this will be human in the loop agent. Not full automation |  | Simulates the human city reviewer: walks the design wall by wall (or constraint by constraint) and asks “does this meet requirements?” for each element, producing a sign off trail, this is the human in the loop persona the mentor described as reviewing “every single wall.” | Must let a reviewer step through each structural element (wall, room, setback) individually and approve/reject it, not just approve the whole design at once. Must cross check every element against the same constraint set the Verifier Agent used, so city review and internal verification can never silently disagree. Must reject designs that violate environmental/zoning constraints outright (the mentor was explicit: environmental violations are not approved, full stop). Must produce an auditable sign off record per element that feeds into the Report Generation/PDF output for submission to the permitting office. | ☐ Reviewer can approve/reject each wall or constraint element individually, not just the whole design at once ☐ Every element is cross-checked against the same constraint set the Verifier Agent used — zero disagreement between the two ☐ Any environmental/zoning violation results in automatic rejection — no override path for non-compliant designs ☐ Produces an auditable, element-by-element sign-off record ☐ Sign-off record feeds directly into Report Generation/PDF output ☐ Reviewer can complete a full walkthrough of a standard design in under 10 minutes
Side Views Generation Agent | P0 | Dhwani | [6 empty] | Generates the side elevation views of the house (front/side facades) as a companion output to the floor plan, so the submission package shows the building from multiple angles, not just top down. | Must derive side views directly from the same verified footprint and floor data used by the Floor Plan Generator, never from a separately re generated layout, to avoid drift between views. Must reflect the actual elevation/height design (see Elevation Agent) including any slope driven foundation height changes. Must be exportable into the same PDF/DXF report pipeline as the floor plan and roof plan so the city submission is one consistent package. Must update automatically if the underlying floor plan changes during the Generator↔Verifier loop, rather than going stale. | ☐ Side views are derived directly from the same verified footprint/floor data — never a separately re-generated layout ☐ Reflects actual elevation/height design, including slope-driven foundation height changes ☐ Exportable into the same PDF/DXF pipeline as floor plan and roof plan ☐ Auto-updates if the underlying floor plan changes during the Generator↔Verifier loop — never goes stale ☐ All four sides (front, rear, two sides) generated, not just the front facade
Roof Plan Agent | P0 | Ojas | [6 empty] | Generates the roof layout/plan as its own deliverable on top of the floor plan and elevations, since roofing has its own geometry (pitch, drainage, overlap with walls below) distinct from the floor below it. | Roof footprint must match the top floor footprint boundaries exactly (no overhang errors, no gaps) so it's structurally consistent with the floor plan beneath it. Must account for multi floor and uneven elevation designs (e.g. stepped roofs over a garage in lower lot scenario described in the meeting) rather than assuming a flat single floor roof. Must be included as a distinct artifact in the report/PDF generation output, separate from the floor plan and side views. Must respect any fire safety/setback requirements that apply to roof structures, per the permits discussion. | ☐ Roof footprint matches the top-floor footprint boundaries exactly — no overhang errors, no gaps ☐ Handles multi-floor and uneven-elevation designs (e.g. stepped roof over garage-in-lower-lot) — not hardcoded to flat single-floor assumption ☐ Included as its own distinct artifact in PDF/DXF output, separate from floor plan and side views ☐ Respects fire-safety/setback requirements applicable to roof structures ☐ Roof pitch and drainage direction specified, not just a flat outline
Livabiltity agent | P1 | Aadi | Shreyas | [5 empty] | A non functional requirements agent dedicated to comfort/quality of life checks, daylight, airflow, that the mentor explicitly called out as missing and asked to be a separate agent rather than folded into the Verifier. | Must independently score or flag daylight access and airflow/cross ventilation for every habitable room, separate from the hard legal constraints the Verifier Agent checks. Must run after the Floor Plan Generator produces a candidate layout, and feed soft constraint feedback back into the generation loop (not just a pass/fail). Must surface livability scores in the final report so the homeowner can see comfort quality, not just legal compliance. Must remain a standalone agent (per the mentor's explicit instruction: “I want to have a separate agent there”) rather than being merged into the Constraint or Verifier agents. | ☐ Daylight access is scored/flagged independently for every habitable room ☐ Airflow / cross-ventilation is scored/flagged independently for every habitable room ☐ Runs after Floor Plan Generator produces a candidate layout — not before ☐ Feeds soft-constraint feedback back into the generation loop (not just a pass/fail flag) ☐ Livability score is visible in the final report to the homeowner, separate from legal-compliance status ☐ Remains a standalone agent — not merged into Constraint or Verifier agents. Also integrate Vaastu constraints for livability score(walk score/school score etcetera)
Elevation Agent | P0 | Devam | Marjit |  |  | Devam: Q2. Elevation Agent Output Schema What is the expected handoff format from Elevation Agent to Multi-floor Generator and Side Views Agent? * Structured numeric values only? * Numeric values plus explanatory reasoning? * Additional report-generation metadata? Q1. Elevation Threshold Validation Is the current ">10 ft elevation difference" threshold for triggering split-level or uneven-lot handling finalized, or is it a placeholder requiring validation against real-world lot data? | Q1: good question. Focus on flat lot for now. Split lot requires special handling and we can take it in the next iteration. Q2: Anupam? |  | Handles the height/elevation design problem the mentor flagged as completely uncovered: since no lot is ever flat, this agent figures out foundation height, how much to dig down or build up, and whether to add fill material before the floors above can be built. | Must read actual lot topology (slope, high/low points) before any height decision is made, the mentor was explicit that you “must know about the land” to determine height feasibility. Must support both foundation strategies discussed: digging down for a deeper foundation, or elevating with added fill, and must be able to recommend one over the other with reasoning. Must support the uneven lot/split level case described in the meeting (garage built into the lower part of a sloped lot, house built above it) without being hardcoded to flat lot assumptions. Must hand off final foundation/floor heights to the Multi floor Generator and Side Views agents so all downstream geometry is consistent. | ☐ Reads actual lot topology (slope, high/low points) before making any height decision ☐ Supports “dig down for deeper foundation” as a strategy option ☐ Supports “elevate with added fill material” as a strategy option ☐ Can recommend one strategy over the other with stated reasoning, not just a default choice ☐ Supports uneven-lot / split-level case (e.g. garage built into lower part of sloped lot, house above it) ☐ Hands off final foundation/floor heights to Multi-floor Generator and Side Views agents — both stay consistent with this output
Location Zoning Agent | P0 | Kavya | Prem | [5 empty] | Provides location specific regulatory settings, e.g. Bellevue vs. Seattle Downtown SBC offsets, so every other agent applies the right setbacks, coverage caps, and zoning rules for the actual jurisdiction instead of one hardcoded ruleset. | Must correctly resolve a given address/lot to its jurisdiction and load the matching constraint set (front/rear/side setbacks, max lot coverage, tree protection rules), this directly mirrors Swara's original presentation point about separating constraints by area (Bellevue, Seattle Downtown, etc). Must expose these values to the Constraint Agent and Site Plan Generator Agent as structured data, not free text, since multiple Prob1 findings showed text/image based constraint reading caused misinterpretation. Must support jurisdictions beyond the two already tested (Bellevue, Seattle) without a code rewrite. Must flag clearly when a lot falls in a zone with no constraint data loaded yet, rather than defaulting silently to a wrong ruleset. | ☐ Correctly resolves a given address/lot to its jurisdiction ☐ Loads the matching constraint set: front/rear/side setbacks, max lot coverage, tree protection rules ☐ Constraint data exposed as structured data (JSON), never free text or image ☐ Supports at least the two tested jurisdictions (Bellevue, Seattle Downtown) without code rewrite for additional ones ☐ Clearly flags when a lot falls in a zone with no constraint data loaded — never silently defaults to a wrong ruleset ☐ Lookup response time < 3 seconds per address
Constraint Agent | P0 | Harshit | Dhwani | Ojas | Rohan |  |  |  | Owns the deeper, system level rules engine the mentor distinguished from the Planning Agent: not “how big do you want your house” but “what is the minimum bedroom size, does it need a bathroom, does it connect to a hallway”, every entity in the design has its own constraint set here. | Must maintain a constraint definition for every entity type in the system (room, wall, setback, tree zone, etc.), not just the building envelope, this was the mentor's explicit distinction from the Planning Agent. Must be queryable by both the Generator and Verifier agents so both sides of the loop reference the exact same constraint source (avoiding the drift several Prob2 groups hit when adjacency rules weren't centrally defined). Must support per jurisdiction overrides fed in by the Location Zoning Agent. Must be extensible, new constraint types (fire safety, mechanical room sizing) must be addable without touching agent code, since the constraint list was explicitly called a living, growing list in the meeting. | ☐ Maintains a constraint definition for every entity type: room, wall, setback, tree zone — not just the building envelope ☐ Queryable by both Generator and Verifier agents from the same single source — no drift between what each side checks ☐ Supports per-jurisdiction overrides fed in by Location Zoning Agent ☐ New constraint types (e.g. fire safety, mechanical room sizing) addable without touching agent code ☐ Minimum bedroom size enforced (specific number agreed with mentor before sprint sign-off) ☐ Every room type has at least one defined adjacency/connectivity rule (e.g. must connect to a hallway)
Rohan?
Tools: | [7 empty] | Anirudh?
Z3 Verifier | P0 | Swara | Ojas |  |  |  |  | Sidak? | The deterministic math solver tool that proves whether a layout satisfies every constraint, used both inside the Verifier Agent and runnable locally, already built by the team and explicitly confirmed in the meeting as living inside the Verifier Agent's scope. | Must return a provable pass/fail per constraint, not a probabilistic guess, this is precisely why it exists alongside the LLM agents, which were shown in Prob1/Prob2 findings to hallucinate on math and flip between conflicting constraints. Must support an “optimize” mode to compute the provable maximum buildable area (as one group used to turn “maximize area” into a hard threshold constraint rather than a vague prompt instruction). Must include floating point tolerance to avoid false negative failures on near exact matches. Must be callable both as a step inside the Verifier Agent's pipeline and as a standalone local script for debugging, per the mentor's confirmation that both modes are valid. | ☐ Returns a provable pass/fail per constraint — never a probabilistic guess ☐ Supports an “optimize” mode that computes the provable maximum buildable area ☐ Floating-point tolerance configured to avoid false-negative failures on near-exact matches ☐ Callable as a step inside the Verifier Agent's pipeline ☐ Callable standalone, locally, for debugging outside the full pipeline ☐ Solve time for a standard single-floor layout < 5 seconds ☐ OPEN DECISION (resolve before building further): constraint design must be either (A) hardcoded per-city logic (switch/case per supported city) or (B) config-driven JSON constraint file, modular and city-agnostic — team must explicitly choose one and document why ☐ Called by Site Plan Agent (and other generators) as a direct tool call, NOT routed through the Agent Manager — confirm this tool-call boundary is implemented correctly
Entity Constraint Engine | P0 | Harshit | Anshul | Ojas | Rohan | Anshul: Q1. If a user wants to add some constraints regarding the room layout, or any request which do not agree with existing constraints, will these additional constraints also be part of the constraint engine. | Q1: constraints are system and user defined. If there is conflicts in user defined constraints, this needs to involve Human In Loop to resolve. | Devank? | The execution layer behind the Constraint Agent: this is literally where per entity rules (bedroom minimum size, adjacent room rules, hallway connection requirements) get encoded and checked for every entity in the design. | Must encode constraints at the entity level (per room, per wall, per fixture) so a new entity type can have its own rule set without touching unrelated entities' rules. Must support relational constraints between entities (adjacency, connectivity to hallway, “must have a bathroom nearby”), not just single entity size/shape rules, since this was the specific gap the mentor called out (“what are the adjacent things you can have in a bedroom”). Must be the single source of truth consumed by both the Floor Plan Generator and the Verifier Agent's Z3 checks. Must be versionable so constraint changes can be tracked as the rule set grows over the project. | ☐ Constraints encoded at entity level (per room, per wall, per fixture) independently ☐ New entity type can get its own rule set without touching unrelated entities' rules ☐ Supports relational constraints between entities (adjacency, connectivity to hallway, “must have nearby bathroom”) ☐ Acts as single source of truth consumed by both Floor Plan Generator and Verifier Agent's Z3 checks ☐ Constraint set is versioned — changes are tracked over time, not silently overwritten
Topography | P1 | Devam | Marjit |  |  | Devam: Q1. Availability of Topography Data Does topology/elevation information (slope, contours, high/low points) come bundled with the site engineer report, or is it typically delivered as a separate topographic survey that may not always be available? | Q1: yes bundled |  | Supplies the raw land shape data (slope, elevation contours, high/low points) that the Elevation Agent needs to make foundation height decisions, without this, elevation design has no real input to work from. | Must provide elevation/contour data for a given lot in a structured, queryable format (not just an image), consistent with the project's general finding that coordinate/text input outperforms image input for every downstream agent. Must flag lots with significant unevenness (e.g. >10ft difference across the lot) since this triggers the special case multi height/split level/basement design path discussed in the meeting. Must integrate directly with the Elevation Agent and Multi floor Generator Agent so height decisions and floor stacking decisions are based on the same ground truth. Must degrade gracefully (clear “data unavailable” signal) rather than assuming a flat lot when topography data is missing. | ☐ Provides elevation/contour data for a given lot in structured, queryable format — not an image ☐ Flags lots with significant unevenness (e.g. >10ft difference across the lot) ☐ Integrates directly with Elevation Agent and Multi-floor Generator Agent ☐ Degrades gracefully with a clear “data unavailable” signal — never silently assumes a flat lot ☐ Data freshness/source documented (so the team knows how current the topo data is)
Location Toolkit | P0 | Siddh | Devam |  |  | Devam: Q1. Lot Boundary Classification Does lot CAD input carry front/rear/side edge classification (i.e., which boundary segments correspond to which setback type), or is it raw unlabeled geometry? If unlabeled, which component is responsible for resolving this: Location Toolkit, Location Zoning Agent, or Site Plan Generator? Q2. Multiple Frontages Can a single lot have more than one "front" (e.g., corner lots with dual street frontage)? If yes, is this already handled within the setback rule framework, or does it require separate logic? Q3. Front/Rear Classification Ownership Which component owns front/rear/street-facing edge classification: Location Toolkit or Location Zoning Agent? Q4. Lot Boundary Format from Location Toolkit Does Location Toolkit provide lot boundaries in line-and-arc metes-and-bounds format, or are curved segments already densified into polygons before handoff? | Q1: unlabeled. Needs discussion. Take this up with Anupam in the call. Q2: |  | The general purpose location utility referenced alongside the Z3 Verifier as one of the core tools, supports lookups like address to coordinates and lot boundary retrieval that other agents (especially Location Zoning Agent and Site Plan Generator) depend on. | Must resolve an address or lot reference into precise boundary coordinates usable directly by the Site Plan Generator Agent. Must supply this data in the typed/coordinate format the whole pipeline favors, since image based lot inputs were repeatedly shown to cause misreads. Must support lookups for any jurisdiction the Location Zoning Agent might need, not just the two test jurisdictions used in Prob1/Prob2. Must cache results for performance (works with the Caching/perf backlog item) since repeated lookups of the same lot shouldn't hit external services every time. | ☐ Resolves an address/lot reference into precise boundary coordinates usable by Site Plan Generator Agent ☐ Supplies data in typed/coordinate format, never image-based lot input ☐ Supports lookups beyond the two test jurisdictions used in Prob1/Prob2 ☐ Caches results so repeated lookups of the same lot don't re-hit external services every time ☐ Lookup response time < 3 seconds
PDF generation (report) | P0 | Aayush | Anirudh | [5 empty] | Converts the final verified design into the submission ready PDF report for the city, explicitly called out as a separate functional block needed beyond just the raw DXF export, so users have something readable to submit and share. | Must include more than just the DXF geometry: per room area, dimensions, and other summary data the mentor specifically asked for beyond the raw file. Must support generating different report variants for different construction phases (foundation, framing, etc.), per the team's own suggestion. Must incorporate the Reviewer Agent's element by element sign off trail so the report is submission ready, not just a visual export. Must be regenerable on demand as a “preview” before final submission, supporting the preview tool requirement raised in the meeting. | ☐ Includes per-room area and dimensions, not just the raw DXF geometry ☐ Supports generating different report variants for different construction phases (foundation, framing, etc.) ☐ Incorporates the Reviewer Agent's element-by-element sign-off trail ☐ Regenerable on demand as a “preview” before final submission ☐ Report generation time < 15 seconds for a standard single-floor design ☐ Output is print-ready / matches standard city submission formatting expectations ☐ Minimum image resolution of 300 DPI for all plan/elevation graphics in the report ☐ All doors and windows are individually labeled in the output drawing ☐ Directional labels (N/S/E/W orientation) are present on every plan view ☐ Detailing/labeling style benchmarked against real floor-plan sites (e.g. CommonFloor, MagicBricks) — not an arbitrary in-house format ☐ Any AI-generated checklist/detailing item is manually verified and citation-checked before being treated as a final acceptance criterion — not accepted on first generation
CAD file reader | P1 | Siddh | Devam | [5 empty] | Reads existing CAD drawings (e.g. a reference plot or an existing house drawing) so the system can ingest real world design data instead of only generating from scratch. | Must correctly parse plot boundaries and room geometry out of standard CAD formats without requiring manual re entry of coordinates. Must surface parsed data in the same structured coordinate format the rest of the pipeline expects, since Prob1 findings consistently showed models read poorly from images/CAD drawings directly. Must handle the “design similar to a known layout” use case raised in the meeting, ingesting a reference design as the starting point for a new, constraint adjusted generation. Must flag unparseable or corrupted CAD input clearly rather than silently producing an empty or wrong layout. | ☐ Correctly parses plot boundaries out of standard CAD formats without manual re-entry ☐ Correctly parses room geometry out of standard CAD formats ☐ Parsed data surfaced in the same structured coordinate format the rest of the pipeline expects ☐ Supports “design similar to known layout” use case — ingesting a reference design as a generation starting point ☐ Flags unparseable/corrupted CAD input clearly — never silently produces an empty or wrong layout
DXF file reader | P0 | Sidak | Saksham | [5 empty] | Reads back DXF files already produced by the pipeline (or supplied by a user) so layouts can be re ingested, compared, or used as a base for iteration, distinct from the CAD reader, focused specifically on the DXF format the team already standardized on for output. | Must accurately extract room labels, coordinates, and layer data from DXF files produced by the DXF Generator tool, forming a clean round trip (generate → export → re read) with no data loss. Must support extracting room boundary coordinates for re verification by the Z3 Verifier, mirroring the workflow several groups already built (DXF → read coordinates → verify). Must handle multiple layer/label conventions gracefully, since different generator agents may label rooms slightly differently. Must integrate with the Json Extractor so DXF data can be converted into the JSON format the Verifier Agent consumes. | ☐ Accurately extracts room labels, coordinates, and layer data from DXF files produced by DXF Generator ☐ Round-trip (generate → export → re-read) produces zero data loss ☐ Supports extracting room boundary coordinates for re-verification by Z3 Verifier ☐ Handles multiple layer/label naming conventions across different generator agents ☐ Integrates with Json Extractor to convert DXF data into Verifier-ready JSON
DXF Generator | P0 | Harshit | Devam |  |  | Devam: Q1. Vertex ID Preservation Does the DXF Generator need named shell vertex IDs preserved through to the DXF output, or are final coordinates alone sufficient? Q2. Elevation Dependency for DXF Does the DXF Generator require height information from Elevation Agent for z-axis annotations, or is the current scope limited to a purely 2D footprint? | 1. Yes it'll be good 2. They are 2D, elevation is required for side views |  | Produces the final DXF (CAD) output file from verified coordinates, this is the team's existing, working deliverable, already shown to produce well labelled, dimensioned drawings when fed clean coordinate input. | Must produce DXF output only from already verified coordinates (post Z3 pass), never from unverified Generator Agent output directly, to avoid shipping a non compliant design. Must include room labels and dimensions in the output, since the difference between a labelled and unlabelled DXF was repeatedly flagged as a quality differentiator in Prob1 findings. Must support multi floor, roof, and side view exports as distinct DXF layers/files, not just the single top down floor plan. Must remain deterministic, same verified coordinate input always produces the same DXF output, with no LLM involved at this final export step. | ☐ Only produces DXF output from already-verified (post Z3 pass) coordinates — never from unverified Generator output ☐ Includes room labels in the output ☐ Includes dimensions in the output ☐ Supports multi-floor, roof, and side-view exports as distinct layers/files ☐ Fully deterministic — same verified input always produces the same DXF output, no LLM involved at this step
Json Validator | P0 | Devank | Prasad |  |  | Prasad: If the agents themselves are supossed to generate the output in the required format, what is the role of the json extractor? | Anupam? |  | The translator tool that extracts a generator agent's output into a clean JSON file the Verifier Agent (and its Z3 solver) can consume directly, created specifically to close the gap one group identified between “what Agent 1 generated” and “what Z3 needs to check.” | Must convert generator output (coordinates, room data) into a well formed JSON file on every iteration of the generate verify loop, not just the final pass. Must preserve full fidelity of the original coordinates/labels with no rounding or truncation that could cause false verifier failures. Must be callable automatically as part of the Agent Manager's orchestrated pipeline, not as a manual step. Must handle malformed generator output gracefully (e.g. flag it back to the Generator Agent) rather than producing invalid JSON that silently breaks the Verifier. | ☐ Converts generator output into well-formed JSON on every iteration of the generate-verify loop, not just the final pass ☐ Preserves full coordinate/label fidelity — no rounding or truncation that could cause false verifier failures ☐ Callable automatically as part of the Agent Manager's orchestrated pipeline, not a manual step ☐ Flags malformed generator output back to the Generator Agent rather than producing invalid JSON that silently breaks the Verifier ☐ OPEN QUESTION (must be resolved with Chandra before further build-out): scope of this role vs. Pydantic-based output validation needs clarifying — confirm whether Json Extractor and Pydantic validation are doing different jobs or duplicating each other ☐ Per the Pydantic pattern agreed for all agents: if an agent's output is non-compliant, the agent's own LLM must be given feedback to reformat — invalid output should be resolved INSIDE the agent before it ever reaches the Agent Manager
Gaurdrail Tools | P0 | Swara | [6 empty] | Enforces prompt level safety and legality checks raised directly in the meeting, stopping requests to design illegal/out of code buildings, distinct from authentication, which checks who the user is. | Must block or flag generation requests that explicitly target illegal/non compliant structures, independent of and prior to the Constraint Agent's geometric checks. Must work alongside Authentication/Authorization (a separate block) rather than duplicating it, the mentor was explicit these are two different concerns (who you are vs. what you're allowed to ask for). Must apply consistently across every entry point to the Generator/Planner agents, not just the initial prompt. Must log blocked attempts for audit purposes without exposing internal constraint logic to the end user in a way that helps them circumvent it. | ☐ Blocks/flags generation requests explicitly targeting illegal/non-compliant structures ☐ Runs independently of, and prior to, the Constraint Agent's geometric checks ☐ Operates alongside Authentication/Authorization without duplicating that logic (who you are vs. what you're asking for) ☐ Applied consistently across every entry point to Generator/Planner agents, not just the initial prompt ☐ Logs blocked attempts for audit purposes without exposing internal constraint logic that could help circumvent it
UI
| P0 | Triyansh | Bhavya | Aayush |  | What are the basic element expected in the UI and the flow of it | Good to have a discussion in the call. Work with Anupam. |  | The user facing interface layer connecting the homeowner, architect/reviewer, and city reviewer to the underlying agent pipeline, already prototyped by the team, now needs to support the full set of human in the loop roles identified in the meeting. | Must support three distinct user personas with different views/permissions: homeowner (client), architect/reviewer (human in the loop sign off), and city reviewer (wall by wall approval persona). Must surface the preview tool (view layout before reading full report) and the demo mode (showing prospective users what the system can generate) both explicitly requested in the meeting. Must integrate Authentication/Authorization so only the right user can prompt for their own property's design. Must reflect real time status from the Notification Service so all three personas stay in sync as the pipeline progresses. | ☐ Supports homeowner/client persona view ☐ Supports architect/reviewer (human-in-the-loop sign-off) persona view ☐ Supports city reviewer (wall-by-wall approval) persona view ☐ Includes a preview tool to view the layout before reading the full report ☐ Includes a demo mode for showcasing the system to prospective users ☐ Authentication/Authorization integrated — a user can only prompt for their own property ☐ Reflects real-time status from Notification Service so all personas stay in sync ☐ Page load / interaction response time < 2 seconds
Deployment Engine
| P0 | Saksham | Sidak | [5 empty] | Handles getting the working system out of local scripts/notebooks and into something reliably running and reachable, needed because the team's current Prob1/Prob2 work runs as ad hoc local Python/notebook pipelines, not a deployed product. | Must package the multi agent pipeline (Planner, Generator, Verifier, Constraint, Reviewer agents, etc.) into a deployable service, not a collection of standalone scripts. Must support the API key/cost control concerns already raised (rate limits, quota exhaustion hit by multiple groups during testing) via the Optimizations/Keys/Auth block. Must support redeployment without downtime as agents are iterated on independently, given how actively each agent is still changing. Must expose health/status so the Agent Manager and UI can detect and surface pipeline failures rather than hanging silently. | ☐ Packages the full multi-agent pipeline as one deployable service, not standalone scripts ☐ Supports API key rotation/fallback and rate-limit handling (ties to Optimizations/Keys/Auth) ☐ Supports redeployment without downtime as individual agents are iterated on ☐ Exposes health/status endpoint so Agent Manager and UI can detect pipeline failures ☐ Rollback to previous stable version possible within minutes if a deployment breaks ☐ Evaluated against at least 3 concrete options — Vercel, Render, Railway — with a documented reason for the final pick ☐ If Vercel is chosen: confirmed the project fits inside the free-tier 2 GB limit, or a paid tier is budgeted for ☐ Kubernetes and Docker containerization reviewed explicitly as part of the deployment approach, not skipped ☐ Entry point structure confirmed (app.py / main.py importing modules) — matches the agreed repo folder structure doc
Database
| P0 | Swara | Prem | [5 empty] | Persistent storage for user outputs, conversation memory, and caching, raised early in the meeting as a clear gap (“we need a database so the user can store their outputs”) and confirmed to also house both short/long term memory and the caching layer. | Must persist every user's generated layouts and reports so they can return to past sessions, per the original requirement. Must store conversation/session memory (short term and long term) so context isn't lost between generator verifier iterations, as confirmed by the mentor in the meeting. Must keep all user data private by default, explicitly confirmed in the meeting that other users must never see someone else's house layout. Must support the caching/performance layer as a sub component, so repeated lookups (location data, prior iterations) don't require full recomputation. | ☐ Persists every user's generated layouts and reports across sessions ☐ Stores conversation/session memory (short-term and long-term) ☐ User data is private by default — one user can never see another user's house layout ☐ Caching/performance layer implemented as a sub-component of the database, not a separate system ☐ Query/read response time < 1 second for retrieving a saved design ☐ Relational data (user accounts, project records, structured fields) stored in Supabase (Postgres) ☐ Vector data (embeddings for RAG/similarity/memory search) stored in Qdrant, chosen specifically for speed, open-source licensing, and rich metadata tagging support ☐ Clear, documented split between what goes in long-term memory vs. short-term memory vs. the vector DB — not an ad hoc per-agent decision
End-End Validation + Agentic + Scenario
| P0 | Marjit | Shreyas | [5 empty] | The full pipeline test harness: runs realistic end to end scenarios through every agent in sequence to confirm the whole system (not just individual agents) produces a compliant, submittable design. | Must run complete scenarios covering the functional goals list as it stood at the end of the meeting: report generation, report submission, reviewer persona sign off, cost estimation, multi phase reports, and the demo flow. Must catch integration failures between agents (e.g. Elevation Agent output not matching what Multi floor Generator expects) that unit level agent testing would miss. Must include at least one multi floor and one uneven lot scenario, since these were flagged as the most complex, least validated paths discussed. Must produce a clear pass/fail report per scenario, callable repeatedly as agents change, not a one time manual check. | ☐ Runs complete scenarios covering: report generation, report submission, reviewer sign-off, cost estimation, multi-phase reports, demo flow ☐ Includes at least one multi-floor test scenario ☐ Includes at least one uneven-lot/split-level test scenario ☐ Catches integration failures between agents (e.g. Elevation Agent output not matching Multi-floor Generator's expectations) ☐ Produces a clear, repeatable pass/fail report per scenario — re-runnable as agents change, not a one-time manual check
Market Analysis
| P1 | Shreyas | Marjit | [5 empty] | Research workstream to understand the competitive/market landscape for this product, distinct from the technical build, but needed to validate the product direction the team is building toward. | Must identify existing tools/competitors solving similar house design to permit problems, if any, and where this system's neuro symbolic (LLM + Z3) approach differs. Must inform prioritization decisions (e.g. which functional goals matter most to real users) rather than being a purely academic exercise. Must be kept up to date as the product scope solidifies, since this was flagged P1 rather than P0, useful but not blocking the technical build. Must produce a shareable summary the team can reference when explaining the product's value to mentors or future stakeholders. | ☐ Identifies existing competitors/tools solving similar house-design-to-permit problems ☐ Clearly states where this system's neuro-symbolic (LLM + Z3) approach differs from competitors ☐ Findings inform prioritization of functional goals, not treated as a purely academic exercise ☐ Summary is kept up to date as product scope solidifies ☐ Produces one shareable summary document the team can reference with mentors/stakeholders
LLM
Optimizations/Keys/Auth | P0 | Nitesh | [6 empty] | Manages API key allocation, rate limit handling, and cost/usage optimization across all the LLM calls the pipeline makes, a real, already encountered problem given how many groups hit quota limits and API rate caps during Prob1/Prob2 testing. | Must handle API key rotation/fallback so a single provider's rate limit (a real failure mode multiple groups hit) doesn't stall the entire pipeline. Must track token/request usage per agent so cost estimation and billing (separate backlog items) have real usage data to draw from. Must support swapping the underlying LLM per agent without breaking the pipeline, since nearly every group ended up switching models mid project for cost or reliability reasons. Must keep API keys and credentials secure and never exposed to the end user facing UI. | ☐ API key rotation/fallback in place so one provider's rate limit doesn't stall the entire pipeline ☐ Tracks token/request usage per agent ☐ Supports swapping the underlying LLM per agent without breaking the pipeline ☐ API keys/credentials never exposed to the end-user-facing UI ☐ Usage data feeds Cost Estimation and Billing accurately
Backlog
Templatization | P2 | Rohan | [6 empty] | Lets a user pick a pre defined house template (e.g. “2BHK” or “3BHK”) instead of specifying every layout detail manually, raised directly in the meeting as a customization shortcut tied to the Planning Agent. | Must offer a set of common templates (by BHK count/size) selectable directly from the Planner/Customer Support Agent's intake flow. Must allow a selected template to still pass through the full Constraint Agent and Verifier Agent checks for the specific lot, templates are a starting point, not a bypass of verification. Must support saving a user's finalized design as a new reusable template (the “save templates” idea raised in the meeting) for future use. This is a P2 backlog item, so must not block any P0 agent's development. | ☐ Offers a set of common templates (by BHK count/size) selectable from Planner Agent's intake flow ☐ A selected template still passes through full Constraint Agent and Verifier Agent checks — not a verification bypass ☐ Supports saving a user's finalized design as a new reusable template ☐ Does not block any P0 agent's development (P2 item)
Training w/ Design | P2 | Anshul | [6 empty] | Trains a model/RAG system on a builder's history of prior designs (e.g. 50 previous houses) so new generations match that builder's established style, the “design similar to known layout, at scale” use case discussed at length in the meeting. | Must accept a corpus of a builder's prior designs as training/RAG input, distinct from the one off “copy this single house” similarity case (handled by the Similarity Layout Agent). Must produce new designs that are stylistically consistent with the training corpus rather than generic outputs, per the mentor's framing (“I don't want anything new”). Must clearly use either a RAG approach or a custom trained model per the mentor's explicit suggestion, with that choice documented. This is a P2 backlog item, must not block P0 agent work, but should be designed to plug into the Generator Agent later without a rebuild. | ☐ Accepts a corpus of a builder's prior designs as training/RAG input ☐ Produces new designs stylistically consistent with the training corpus, not generic output ☐ Documented choice of RAG vs. custom-trained model approach ☐ Designed to plug into Generator Agent's existing interface without requiring a rebuild later
User-defined training | P2 | Prem | [6 empty] | Lets an individual end user (not just a builder) feed in their own design preferences or reference designs to bias future generations toward their taste, a lighter weight version of the builder training use case. | Must let a single user supply preference signals (liked layouts, reference images/coordinates) without requiring the full 50 design corpus the builder training case assumes. Must keep this training data scoped privately to that user, consistent with the database privacy requirement already established. Must feed into the same Generator Agent interface as builder trained and default generation, so the pipeline doesn't fork into incompatible paths. This is a P2 backlog item and should not block any P0 work. | ☐ Accepts individual user preference signals without requiring a full design corpus ☐ Training data scoped privately to that single user ☐ Feeds into the same Generator Agent interface as default/builder-trained generation
Retrofitting | P2 | [7 empty] | Out of scope for now capability to modify an existing house (e.g. add a floor) rather than design from scratch, the mentor explicitly called this out as a longer term requirement that's deliberately not prioritized yet. | Must, when eventually built, re evaluate all relevant constraints for the modified structure rather than only checking the new addition in isolation, per the mentor's explicit warning that this is “quite complex.” Must not be started before the core single floor and multi floor generation paths are solid, since it depends on them. Has no assigned priority or owner yet in this sprint, correctly reflects its explicit out of scope status from the meeting. Should be revisited only after P0/P1 items are stable. | ☐ Re-evaluates all relevant constraints for the modified structure, not just the new addition in isolation ☐ Not started before core single-floor and multi-floor generation paths are solid ☐ Explicitly out of scope for this sprint — no owner assigned yet
3D diagrams | P3 | [7 empty] | Produces 3D visualizations of the generated design, beyond the 2D floor plans/elevations/roof plans already in scope, listed as a non functional goal in the original whiteboard. | Must generate a 3D representation directly from the same verified coordinate data used for 2D outputs, not a separately modeled view, to avoid inconsistency between 2D and 3D outputs. Must support viewing the house from multiple angles, addressing the “views of the house” non functional goal noted on the whiteboard. This is a P3 item, should not be started before all P0/P1 agents and tools are functional. Must integrate with the preview tool so 3D views can be part of the pre submission preview, when built. | ☐ 3D representation generated directly from the same verified coordinate data as 2D outputs ☐ Supports viewing the house from multiple angles ☐ Not started before all P0/P1 agents and tools are functional
Interior Design | P3 | [7 empty] | Covers interior design detailing beyond room layout, finishes, fixtures, furnishing level detail, as distinct from the structural Floor Plan Generator Agent's room tiling work. | Must build on top of the already verified room layout from the Floor Plan Generator Agent, not duplicate or override its geometry. Must remain scoped to aesthetic/detailing concerns, leaving all structural/legal compliance to the Constraint and Verifier agents. This is a P3 backlog item, must not be staffed or started before P0 items are complete. Should be designed so it can be skipped entirely without breaking the core report generation flow, since it's a nice to have, not a submission requirement. | ☐ Builds on top of already-verified room layout from Floor Plan Generator Agent — does not duplicate/override geometry ☐ Scoped to aesthetic/detailing only — structural/legal compliance stays with Constraint and Verifier agents ☐ Can be skipped entirely without breaking the core report-generation flow
Billing | P3 | [7 empty] | Handles user facing billing/payment for usage of the product, separate from internal cost/token tracking (Optimizations/Keys/Auth) which is about API cost, not customer billing. | Must track billable usage per user account in a way that's auditable and tied to the Database's per user data model. Must stay cleanly separated from the Optimizations/Keys/Auth block: that tool tracks API/token cost; this one is the customer facing charge. Must integrate with Cost Estimation so a user can see projected cost before committing to a design change. This is a P3 backlog item and must not block any P0/P1 work; explicitly, financial planning and loan processing were called out of scope entirely. | ☐ Tracks billable usage per user account, tied to Database's per-user data model ☐ Stays cleanly separated from Optimizations/Keys/Auth (API cost vs. customer billing) ☐ Integrates with Cost Estimation so user sees projected cost before committing to a change ☐ Financial planning / loan processing explicitly out of scope
Cost Estimation | P3 | Marjit | Kavya | [5 empty] | Gives the homeowner a real cost estimate for their design, and specifically, how cost changes if they add more square footage, raised directly in the meeting as a clear functional gap the team hadn't addressed yet. | Must recompute an estimate when the design changes (e.g. added square footage), not just produce a single static number at the end, per the specific scenario raised in the meeting (“if they add more square feet, how much extra cost”). Must factor in regional cost differences tied to the Location Zoning Agent's jurisdiction data, since cost varies by location. Must feed into Billing for any customer facing charges, while staying distinct from the internal API cost tracking in Optimizations/Keys/Auth. This is a P3 backlog item but was flagged by the mentor as a “very good point”, should be picked up once P0 agents are stable. | ☐ Recomputes estimate when design changes (e.g. added square footage) — not a single static number ☐ Factors in regional cost differences tied to Location Zoning Agent's jurisdiction data ☐ Feeds into Billing for customer-facing charges ☐ Stays distinct from internal API-cost tracking in Optimizations/Keys/Auth
Notification Service | P3 | [7 empty] | Keeps the client, architect, and city reviewer in sync as the pipeline progresses, e.g. notifying everyone when a report has been generated, raised directly in the meeting as a way to connect all three human in the loop personas. | Must trigger notifications to all relevant personas (client, architect/HITL, city reviewer) on key pipeline events such as report generation, verification pass/fail, and reviewer sign off requests, exactly as proposed in the meeting. Must route notifications to the correct persona only, a city reviewer shouldn't get notified about a client's private draft iteration, consistent with the database privacy requirement. Must integrate with the UI so notification state is visible there, not just sent externally (e.g. email). This is a P3 backlog item; should be picked up once the core agent pipeline and UI are stable enough to have meaningful events to notify on. | ☐ Triggers notifications to client, architect/HITL, and city reviewer on key pipeline events (report generated, verification pass/fail, sign-off requested) ☐ Routes notifications only to the relevant persona — city reviewer never sees a client's private draft iteration ☐ Notification state visible in UI, not only sent externally (e.g. email)
RAG | P3 | Nitesh | Swara | [5 empty] | Retrieval augmented generation layer that can ground generation in either external reference material (e.g. SMC/SBC code documents) or a builder's design history, supporting the Training w/ Design use case discussed in the meeting. | Must be able to retrieve relevant constraint/code text from official documents (e.g. zoning code markdown files) to ground agent outputs, rather than relying on the LLM's memorized/possibly outdated knowledge of building codes. Must support retrieval over a builder's historical design corpus, as the concrete realization of the “create a RAG or custom model” suggestion from the meeting. Must integrate with caching (Caching/performance backlog item) so repeated retrievals don't add unnecessary latency. This is a P3 backlog item, should follow, not precede, the core Generator/Verifier loop being solid. | ☐ Retrieves relevant constraint/code text from official documents to ground agent outputs ☐ Supports retrieval over a builder's historical design corpus (Training w/ Design use case) ☐ Integrates with caching so repeated retrievals don't add unnecessary latency
Notification Service | P3 | [7 empty] | Duplicate entry of the Notification Service item above (row 53) in the original sprint sheet, same scope and requirements apply; kept here only because it appears twice in the source sheet. | Same acceptance criteria as the Notification Service entry above (row 53): must notify client, architect/HITL, and city reviewer on key pipeline events, route to the correct persona only, and surface state in the UI. Recommend the team de duplicate this row during sprint grooming so only one owner is assigned and tracked. This is a P3 backlog item. | ☐ Duplicate of row 53 — same checklist applies ☐ Recommend de-duplicating this row during sprint grooming so only one owner is tracked
Caching/performance | P3 | [7 empty] | Improves system responsiveness and lets users resume work where they left off, by caching intermediate results (location lookups, prior generation iterations) instead of recomputing them, raised directly in the meeting as a database sub feature. | Must let a user resume a session from where they left off without re running already completed generation/verification steps, per the original meeting request. Must cache location/topography lookups so repeated queries for the same lot don't re hit external services. Must live as a sub component of the Database, as explicitly clarified in the meeting (“you need a caching under your database”), not as a fully separate system. This is a P3 backlog item, valuable for UX polish once the core pipeline is functionally complete. | ☐ User can resume a session without re-running already-completed generation/verification steps ☐ Location/topography lookups cached so repeated queries for the same lot don't re-hit external services ☐ Lives as a sub-component of the Database, not a fully separate system
Similarity Layout Agent | P3 | [7 empty] | Generates a new design that closely matches a single reference house the homeowner liked (“I want something like this”), adjusting for the new plot's different setbacks, slope, and angle, the one off version of the design similarity use case discussed in the meeting. | Must take a single reference layout/design as input and produce a new design that is similar to it, adapted to the new plot's actual setbacks, elevation, and slope, since the mentor was explicit the new plot will virtually never match the reference exactly. Must clearly communicate to the user when an exact copy isn't feasible and explain what had to change and why, rather than silently producing a different design. Must distinguish this single reference, inference time use case from the Training w/ Design backlog item, which trains on many designs at once. This is a P3 backlog item but should be designed to plug into the Generator Agent's existing interface so it isn't a separate rebuild later. | ☐ Takes a single reference layout as input and produces a new design adapted to the new plot's actual setbacks/elevation/slope ☐ Clearly communicates to the user when an exact copy isn't feasible, and explains what changed and why ☐ Distinguished from Training w/ Design (single-reference, inference-time use, not multi-design training) ☐ Designed to plug into Generator Agent's existing interface
Authorization | P2 | [7 empty] | Confirms the requesting user is authorized to act on a given property/account, the authorization (AuthZ) half of the Authentication/Authorization block raised early in the meeting, distinct from the Guardrail Tools which check what's being asked for, not who's asking. | Must verify a user is authorized to prompt for/modify a specific property's design before any agent processes their request, directly addresses the meeting's concern about a “random hacker” being able to prompt. Must work together with Authentication (verifying identity) as two distinct checks, per the mentor's explicit AuthN/AuthZ distinction. Must integrate with the Database's privacy model so authorization and data access rules are enforced consistently. This is a P2 backlog item, but security related items like this should be prioritized earlier rather than left until last, given the explicit “we need security” concern raised early in the meeting. | ☐ Verifies a user is authorized to prompt for/modify a specific property's design before any agent processes the request ☐ Works alongside Authentication as two distinct checks (identity vs. permission) ☐ Integrates with Database's privacy model for consistent enforcement ☐ Prioritized earlier rather than left until last, given the security concern raised early in the meeting
Deprioritized